## User Stories
Theme | As a/an | I want to... | so that... | Notes | Priority | Status
TGTHR |  | Description: | TGTHR brings people together in thousands of cities to do more of what they want to do in life. It is organized around one simple idea: when we get together and do the things that matter to us, we’re at our best. And that’s what TGTHR does. It helps people meet up, explore, teach and learn the things that help them come alive. | link to diagram
feature - main screen | user | go to a homepage | I will be able to access my account settings, event screen, and map screen. | landing screen | 1, required | not done
subfeature - main screen | user | have a dashboard | I can see upcoming events. | the "event screen" | 1, required | not done
feature - itself | non user | make an account | I can access this service at my leisure without worrying about losing all my settings due to not having an account, and register for events with my friends. I would also like to include my friends, who do not have an account with me on the outing. | register new user | 1, without being able to register for the service users will not be able to use the application at all | not done
subfeature - user setting | user | delete my account | I no longer have an email connected to TGTHR |  | 1, should be able to delete account | not done
sub feature - user setting | registered user | change my password | I can be secure in my online identity, and to prevent other users from stealing my password or being hacked by using a similar password for other services. | Gotta verify email to change password | 2 not 100% necessary to ship, but an important feature to have in any online account | not done
subfeature - user setting | user | receive notifications | I can be reminded of upcoming events |  | 2, not necessary but handy to have | not done
subfunction - user setting | user | use the application in my native language | I can more quickly understand what information the application is giving me. Just because I am on vacation in France does not mean that I know how to speak French, even though all other users around me are using the application in French. | Use phone native language in application | 3, minor inconvienince, but can be overwritten manually if the user does not understand the language installed in. | not done
subfeature - user setting | user | connect with other social platforms | see which friends are using the app and which events they are going to | connectivity | 7, who needs friends | not done
feature - map screen | event host | include event locations in map | others can see where the event is | event page | 2, required | not done
subfeature - event menu | event host | post an event | People can join my event. | post event | 1, required | not done
subfeature - event screen | user | see who is going to an event | See if I know anybody attending the event | event page | 5, not required but nice to have | not done
subfeature - event screen (host) | event host | edit my posted event | I can change make edits to my event if there is anything that needs editing. | edit event | 3, not required but Quality-of-Life (this includes deleting an event) | not done
subfeature - event menu | event host | allow nearby people to join | People that are too far from my event are not able to join | join nearby event | 3, not required | not done
subfeature - event menu | new user | see recommended events | i can go to events based pertaining to certain interests | homepage/ registration | 3, helps the user see what events are around in an organized manner | not done
subfeature - event screen | user | join events | I can tell people that I will be attending the event | join event, database work | 1, required | not done
EXTRAS (Currently Omitted) | [6 empty] | Reason:
sub feature - map screen | registered user | rotate the phone | Use the application in landscape so that I can get a bigger view of the map while planning events. | lol nobody does this | 10, not very important, does not impact usability in any way | not done | Not really important at the moment
subfeature - event screen (host) | event host | delete my event | I can cancel my event because nobody is coming | delete event | 5, not required but will stop flooding of events | not done | Delete event is part of 'edit event'
subfeature - event screen (host) | user | create a group | I can gather people with similar interests together |  | 5 not required | not done | Going for basic functionality first
subfeature - event screen | user | join a group | I can easily find other people with similar interests. |  | 5 not required | not done | Going for basic functionality first
feature - big (main app functionality) | registered user | use the application | I can set up events to go to while on vacation with my friends in a foreign country. I want to open the app and be able to set a radius of potential events to join and pick one based on time conviencience. I want to sort by distance, by time and by activity type. I plan to include my friends, so a number RSVP would be nice (not 100% required) | basic app functionality | 1, lol without the app we have no project so this is a necessity | not done | More of an Epic vs a User Story
feature - event menu | registered user | follow organizations/ hosts | I can keep up-to-date with events they post and get notifications when they post | push notiifications/ homepage | 4, not required if user wants to go to recurring events | not done | Going for basic functionality first
features different screens
subfeatures things on those screens
Note on E2: https://www.lucidchart.com/invitations/accept/1232a780-b021-423e-b47f-1ee174705edd -Sabrina Wong

## README
Last Update | 2018-10-12
Author | Ryan Yuzuki, Apollo Truong, Sabrina Wong, Brandon Tran
Email | ryuzu001@ucr.edu, atruo017@ucr.edu, swong040@ucr.edu, btran022@ucr.edu
Description | This is a SCRUM template designed for our project in CS180, TGTHR. TGTHR brings people together in thousands of cities to do more of what they want to do in life. It is organized around one simple idea: when we get together and do the things that matter to us, we’re at our best. And that’s what TGTHR does. It helps people meet up, explore, teach and learn the things that help them come alive.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress
Track this project on github!

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Homepage | As a registered user, I want to go to a homescreen. Homescreen has buttons or otherwise allows the user to access [account settings, event listings (dashboard), nearby map]. | 8 | 1 | example: snapchat. When you open it, it defaults to the camera screen. This will be our homepage, which allows the user to access other features. From this page, we can access the snapchat conversation menu (dashboard), our snapcode (account settings), or stories page (map page). When you first open TGTHR, we would default to the homepage, which has buttons (or sliding, or whatever) to access account settings, event listings (called the dashboard), or the nearby map. | dashboard is event listing page
2 | Dashboard | As a registered user, I want to be able to have a dashboard so that I can see upcoming events. | 8 | 1 | The dashboard displays event listings. You would be able to sort this in various ways. By distance, time to start, end, duration... etc. | homescreen is landing page
3 | Account Creation | As a non-user interested in the app, I want to make an account so that I can access this service without worrying about losing all my settings due to not having an account, and register for events with my friends. | 7 | 1 | Account creation requires the user to supply name, an email, and a password. An email will be sent whenever the user changes settings under their account screen. | splash screen is shown while app is loading
4 | Account Deletion | As a registered user, I want to delete my account so that I no longer have an email account connected to TGTHR | 3 | 1 | Account deletion requires the user to verify their choice by entering their password. An email will be sent whenever the user changes settings under their account screen.
5 | Password Change | As a registered user, I want to change my password so that I can be secure in my online identity, and to prevent other users from stealing my password or being hacked by using a similar password for other services. | 3 | 2 | Changing password requires the user to input their old password. An email will be sent whenever the user changes settings under their account screen.
|  | TOTAL | 29
Note on C2: Acceptance Criteria: 1. XXX 2. XXX 3. XXX 4. XXX

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
homepage
splash screen
Logout
Login
register new user
profile
map
Task 8: Event Screen | event
Task 9: Edit Setting | edit
Task 9.1: App Setting
Task 9.2: Profile Information
Task 10: View / Host Event
Task 10.1: Host
Task 10.2: View
NOTE *** if there is a task that is too wide, expand it underneath the task (e.g. Task 7.1, ...)
If the task does not exist, please add it :)
EXAMPLE
Task 1: Login Page Design (John Li)
Task 2: Account Table Design (David Brisk)
Task 3: XXX XXX
Task 4: Implement DB for Accounts (Mary Lou)
Task 5: ...
Task 6: ...
Task 7: ...
Task 8: ...
...
Note on C22: Design the login page, including the registration link Acceptance Criteria: 1. XXX 2. XXX
Note on B23: Design a table for storing user accounts Acceptance Criteria: 1. xxx 2. xxx 3. xxx
Note on A24: XXX Acceptance Criteria: 1. XXX 2. XXX
Note on D25: Implement the DB with SQLite based on the design of account table Acceptance Criteria: 1. XXX 2. XXX Verified by: John Li

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Apollo
1 | Apollo
1 | Apollo
1 | Apollo
1 | Apollo
1 | David Hoffman | Task 1: Login Page Design (John Li)
1 | David Hoffman | Task ?
.. | .. | ..
Note on C10: Design the login page, including the registration link

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 0 | 0 | 35 | 35
1 | 35 | 2 | 2 | 33 | 30.625
2 | 36 | 3 | 5 | 31 | 26.25
3 | 36 | 3 | 8 | 28 | 21.875
4 | 36 | 4 | 12 | 24 | 17.5
5 | 34 | 3 | 15 | 19 | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0